## Project Description
Your Name: | Will Fergus
Project Description:
I plan on doing a 2D Xamarin app. I think that 3D would be pushing my comfort zone the most, however I feel that a portfolio piece that shows the ability to publish to multiple platforms is the most relevant in our smartphone driven world. Probably with the inclusion of Lottie examples.

## User Stories
User Stories
UserStory# | StoryName | As a … | I want… | So That… | Status
1 | StartApp | User | To open the app | I can start using it
2 | StopApp | User | To exit the app | I can stop using it
3 | CrossPlat | User | Cross-platform compatability | The app works on the device I'm currently using
4 | UI_Select | User | Selection buttons | I can select an animation
5 | UI_Back | User | A return/back button | I can go back to choosing an animation
6 | LottieDottieDa | The one and only D. O. double G | A reason to open the app | For entertainment? Because its pretty?

## Backlog
Backlog |  |  | (Bug or Task)
Priority | BacklogId | StoryName | BacklogType | Description | In | InSprint
10 | 1 | StartApp | task | Create an app to open(start xamarin project in VS) | someClass.cs
3 | 2 | StopApp | task | Create an quit/exit button
| 3 | StopApp | task | Write an exit method
| 4 | UI_Selection | task | Create buttons that open the corresponding lottie animation
| 5 | UI_Selection | task | Write method to attach buttons to opening an animation
| 6 | UI_Back | task | Create a back/retrun to home button
| 7 | UI_Back | task | Write method to return to home screen
| 8 | LottieDottieDa | task | Find multiple lottie animations to use from the internet
| 9 | LottieDottieDa | task | Get animations working in app
2 | 10 | CrossPlat | task | Make sure xamarin is working properly

## Sprint1_11-19
Sprint 1
Points | BacklogId | StoryName | BacklogType | Description | In
1 | 1 | StartApp | task | Create an app to open(start xamarin project in VS)
2 | 8 | LottieDottieDa | task | Find multiple lottie animations to use from the internet
5 | 9 | LottieDottieDa | task | Get animations working in app
Link to Branch:
Notes from Review:

## Sprint2_11-26
Sprint 2
Points | BacklogId | StoryName | BacklogType | Description | In
3 | 4 | UI_Selection | task | Create buttons that open the corresponding lottie animation | someClass.cs
3 | 5 | UI_Selection | task | Write method to attach buttons to opening an animation
3 | 6 | UI_Back | task | Create a back/retrun to home button
3 | 7 | UI_Back | task | Write method to return to home screen
Link to Branch:
Notes from Review:

## Sprint3_12-3
Sprint 3
Points | BacklogId | StoryName | BacklogType | Description | In
3 | 2 | StopApp | task | Create an quit/exit button | someClass.cs
3 | 3 | StopApp | task | Write an exit method
4 | 10 | CrossPlat | task | Make sure xamarin is working properly
Link to Branch:
Notes from Review:

## Release
Release
Points | BacklogId | StoryName | BacklogType | Description | In
10 | 1 | LoadModel | Bug |  | someClass.cs
3 | 3 | SeeInstructions
2 | 2 | LoadModel
4
Link to Branch:
AFTER SHIPPING, REVIEW MAIN BACKLOG AND MARK STATUS
Notes from Review: