## Project Description
Your Name: | Will Fergus
Project Description:
I plan on doing a cross platform 2D Xamarin app with the inclusion of multiple Lottie examples. Hopefully with some customization specific to the various OS.

## User Stories
User Stories
UserStory# | StoryName | As a … | I want… | So That… | Status
1 | StartApp | User | To open the app | I can start using it
2 | StopApp | User | To exit the app | I can stop using it
3 | CrossPlat | User | Cross-platform compatability | The app works on the device I'm currently using
4 | UI_Select | User | Selection buttons | I can select an animation
5 | UI_Back | User | A return/back button | I can go back to choosing an animation
6 | LottieDottieDa | The one and only D. O. double G | A reason to open the app | For entertainment? Because its pretty?

## Backlog
Backlog |  |  | (Bug or Task)
Priority | BacklogId | StoryName | BacklogType | Description | In | InSprint
10 | 1 | StartApp | task | Create an app to open(start xamarin project in VS) |  | 1
4 | 2 | StopApp | task | Create an quit/exit button |  | 3
4 | 3 | StopApp | task | Write an exit method |  | 3
4 | 4 | UI_Selection | task | Create buttons that open the corresponding lottie animation |  | 2
4 | 5 | UI_Selection | task | Write method to attach buttons to opening an animation |  | 2
4 | 6 | UI_Back | task | Create a back/retrun to home button |  | 2
4 | 7 | UI_Back | task | Write method to return to home screen |  | 2
6 | 8 | LottieDottieDa | task | Find multiple lottie animations to use from the internet |  | 1
6 | 9 | LottieDottieDa | task | Get animations working in app |  | 1
2 | 10 | CrossPlat | task | Make sure xamarin is working properly in various OS |  | 3
1 | 11 | CrossPlat | task | Tailor UI specifically for the various OS |  | Release

## Sprint1_11-19
Sprint 1
Points | BacklogId | StoryName | BacklogType | Description | In
1 | 1 | StartApp | task | Create an app to open(start xamarin project in VS)
2 | 8 | LottieDottieDa | task | Find multiple lottie animations to use from the internet
5 | 9 | LottieDottieDa | task | Get animations working in app
Link to Branch:
Notes from Review:

## Sprint2_11-26
Sprint 2
Points | BacklogId | StoryName | BacklogType | Description | In
3 | 4 | UI_Selection | task | Create buttons that open the corresponding lottie animation
3 | 5 | UI_Selection | task | Write method to attach buttons to opening an animation
3 | 6 | UI_Back | task | Create a back/retrun to home button
3 | 7 | UI_Back | task | Write method to return to home screen
Link to Branch:
Notes from Review:

## Sprint3_12-3
Sprint 3
Points | BacklogId | StoryName | BacklogType | Description | In
3 | 2 | StopApp | task | Create an quit/exit button
3 | 3 | StopApp | task | Write an exit method
3 | 10 | CrossPlat | task | Make sure app opens in Android
3 | 10 | CrossPlat | task | Make sure app opens in WinForms
3 | 10 | CrossPlat | task | Make sure app opens in iOS
Link to Branch:
Notes from Review:

## Release
Release
Points | BacklogId | StoryName | BacklogType | Description | In
5 | 11 | CrossPlat | task | Customize UI specifically for Android
5 | 11 | CrossPlat | task | Customize UI specifically for iOS
5 | 11 | CrossPlat | task | Customize UI specifically for WinForms
Link to Branch:
AFTER SHIPPING, REVIEW MAIN BACKLOG AND MARK STATUS
Notes from Review: